## Resource Plan
Resource Planning Sample - Team Capacity and Allocation
Planning Period | Jul-2026 to Sep-2026 |  | Target Utilization | 80% |  | Bench Threshold | 15%
Employee | Role | Skill | Location | Monthly Capacity (hrs) | Project | Allocation % | Allocated Hrs | Available Hrs | Utilization Status
An Nguyen | Data Analyst | Power BI / Excel | Ho Chi Minh City | 160 | Resource Planning Dashboard | 75%
Binh Tran | Backend Engineer | Python / API | Ho Chi Minh City | 160 | Permission Audit Tool | 90%
Chi Le | PM | Planning / Reporting | Ho Chi Minh City | 160 | Haskoning PMO | 65%
Duong Pham | Data Engineer | SQL / ETL | Ho Chi Minh City | 168 | Resource Planning Dashboard | 85%
Huy Vo | QA Engineer | Testing / Automation | Ho Chi Minh City | 160 | Folder Governance | 55%
Linh Ho | Business Analyst | Process / Reporting | Ho Chi Minh City | 160 | Internal KPI Dashboard | 40%
Minh Do | Frontend Engineer | Streamlit / UI | Ho Chi Minh City | 160 | Internal KPI Dashboard | 95%
Phuc Nguyen | Support Engineer | Ops / Access | Ho Chi Minh City | 168 | Permission Audit Tool | 60%
Quynh Bui | Consultant | Planning / Client Ops | Ho Chi Minh City | 160 | Haskoning PMO | 70%
Tam Truong | Developer | Python / Automation | Ho Chi Minh City | 160 | Image Share Tool | 50%
Tuan Le | Data Analyst | Excel / Forecasting | Ho Chi Minh City | 160 | Resource Planning Dashboard | 100%
Vy Tran | Designer | UX / Reporting | Ho Chi Minh City | 152 | Internal KPI Dashboard | 35%
Dashboard KPIs
Total Capacity Hrs
Total Allocated Hrs
Overall Utilization
Bench Risk Count
Overallocated Count
Assumptions / Notes
- Monthly capacity excludes public holidays and leave.
- Allocation % is the primary user input for scenario planning.
- Bench Risk means remaining capacity above threshold and below target utilization.
- Overallocated means allocation exceeds 100%.
Note on A1: Sample workbook generated for internal resource planning demonstration.
Note on B2: Illustrative planning horizon only. Replace with actual period.
Note on E2: Target utilization assumption. Adjust for your operating model.

## Summary
Resource Planning Summary
Project | Team Members | Capacity Hrs | Allocated Hrs | Avg Allocation % | Available Hrs
Folder Governance
Haskoning PMO
Image Share Tool
Internal KPI Dashboard
Permission Audit Tool
Resource Planning Dashboard

## Deploy Architecture
Recommended Deployment Architecture for Internal Resource Planning Data
Layer | Component | Purpose | Recommended Choice | Notes | Security | Ops
Source Data | Excel workbook / SharePoint folder | Business-owned planning input | Store workbook in SharePoint/OneDrive versioned folder | Business team updates template monthly | M365 permissions by team | Low ops
Ingestion | Python pandas/openpyxl loader | Read workbook and validate schema | Load xlsx on app startup or scheduled refresh | Reject invalid columns / missing sheets | Read-only service access | Medium
App Layer | Streamlit dashboard | Interactive filters, KPIs, charts, export | Dockerized Streamlit app on internal VM/App Service | Cache data and support file refresh | SSO / OIDC + VPN or private network | Medium
Auth | Microsoft Entra ID | Identity and access control | OIDC login for internal users | Restrict to company tenant/group | MFA + group-based access | Low
Reverse Proxy | Nginx or App Gateway | TLS termination and routing | Expose only internal HTTPS endpoint | Optional path-based routing | HTTPS, headers, IP allowlist | Medium
Container Runtime | Docker | Portable deployment | Single container per environment | Dev/Test/Prod image tags | Secrets via env vars | Medium
Monitoring | Application logs + health check | Support and troubleshooting | Health endpoint and structured logs | Track refresh failures | No secrets in logs | Medium